## Product Backlog
CyberShield SOC — Product Backlog
Project: CyberShield SOC ¦ Start: 05-Feb-2026 ¦ Sprints: 8 ¦ Team: Joshitha Mugunthan,Trisha L,Banumathi, Manasa Barik, Sadi Soni, Suhas Amane, Ashwath, Ajay Varande, Snehitha Krishna, Priya Barad
Project Link:
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW Priority | Dependency | Assigned Members | Story Points | Status
Sprint 1 | Sprint 1 | CS-001 | Define project scope and security objectives for SOC platform | MUST HAVE | None | Snehitha Krishna , Joshitha Mugunthan | 3 | 3 - Completed
Sprint 1 | Sprint 1 | CS-002 | Set up GitHub repository and configure branch protection rules | MUST HAVE | CS-001 | Manasa Barik , Suhas Amane | 2 | 3 - Completed
Sprint 1 | Sprint 1 | CS-003 | Finalize tech stack: React 18, Node.js, MongoDB Atlas, Socket.IO | MUST HAVE | CS-001 | Ajay Varande , Trisha L | 3 | 3 - Completed
Sprint 2 | Sprint 2 | CS-004 | Design MongoDB schema for threats, alerts, and incident records | MUST HAVE | CS-003 | Priya Barad , Banumathi , Sadi Soni | 5 | 3 - Completed
Sprint 2 | Sprint 2 | CS-005 | Implement JWT-based login and role management (Admin / Analyst) | MUST HAVE | CS-003 | Ashwath , Snehitha Krishna , Joshitha Mugunthan | 8 | 3 - Completed
Sprint 2 | Sprint 2 | CS-006 | Build REST API skeleton with Express.js and connect to MongoDB Atlas | MUST HAVE | CS-004 | Manasa Barik , Suhas Amane | 6 | 3 - Completed
Sprint 3 | Sprint 3 | CS-007 | Integrate AbuseIPDB API to fetch blacklisted IP reputation data | MUST HAVE | CS-006 | Ajay Varande , Trisha L | 5 | 3 - Completed
Sprint 3 | Sprint 3 | CS-008 | Create threat simulation engine to generate dummy attack events | MUST HAVE | CS-006 | Priya Barad , Banumathi | 8 | 3 - Completed
Sprint 3 | Sprint 3 | CS-009 | Build Socket.IO layer for real-time threat broadcasting to dashboard | MUST HAVE | CS-008 | Sadi Soni , Ashwath , Snehitha Krishna | 8 | 3 - Completed
Sprint 4 | Sprint 4 | CS-010 | Develop interactive global threat map using Leaflet.js and GeoIP data | MUST HAVE | CS-009 | Joshitha Mugunthan , Manasa Barik | 8 | 3 - Completed
Sprint 4 | Sprint 4 | CS-011 | Build security analytics dashboard with Recharts (attack trends, severity) | MUST HAVE | CS-009 | Suhas Amane , Ajay Varande | 8 | 3 - Completed
Sprint 4 | Sprint 4 | CS-012 | Implement automated alert system with configurable threshold rules | MUST HAVE | CS-007 | Trisha L , Priya Barad | 6 | 3 - Completed
Sprint 5 | Sprint 5 | CS-013 | Add MITRE ATT&CK framework tagging to detected threat events | SHOULD HAVE | CS-007 | Banumathi , Sadi Soni | 5 | 3 - Completed
Sprint 5 | Sprint 5 | CS-014 | Develop Nmap-based network vulnerability scanner module | MUST HAVE | CS-006 | Ashwath , Snehitha Krishna , Joshitha Mugunthan | 8 | 3 - Completed
Sprint 5 | Sprint 5 | CS-015 | Build IP reputation lookup page with historical attack metadata | MUST HAVE | CS-007 | Manasa Barik , Suhas Amane | 6 | 3 - Completed
Sprint 6 | Sprint 6 | CS-016 | Integrate QR code and URL threat scanner using VirusTotal API | SHOULD HAVE | CS-007 | Ajay Varande , Trisha L | 5 | 3 - Completed
Sprint 6 | Sprint 6 | CS-017 | Add Gemini-powered AI assistant for SOC analyst query support | MUST HAVE | CS-006 | Priya Barad , Banumathi | 8 | 3 - Completed
Sprint 6 | Sprint 6 | CS-018 | Implement RAG pipeline with local knowledge base for AI responses | SHOULD HAVE | CS-017 | Sadi Soni , Ashwath | 8 | 3 - Completed
Sprint 7 | Sprint 7 | CS-019 | Containerize full application using Docker and Docker Compose | MUST HAVE | CS-018 | Snehitha Krishna , Joshitha Mugunthan , Manasa Barik | 5 | 3 - Completed
Sprint 7 | Sprint 7 | CS-020 | Configure Nginx reverse proxy for production-grade routing | MUST HAVE | CS-019 | Suhas Amane , Ajay Varande , Trisha L | 4 | 3 - Completed
Sprint 7 | Sprint 7 | CS-021 | Build role-based dashboard views (Admin sees all; Analyst sees assigned) | MUST HAVE | CS-005 | Priya Barad , Banumathi | 8 | 3 - Completed
Sprint 8 | Sprint 8 | CS-022 | Optimize MongoDB queries with indexing for high-frequency threat data | SHOULD HAVE | CS-004 | Sadi Soni , Ashwath | 5 | 3 - Completed
Sprint 8 | Sprint 8 | CS-023 | Conduct full end-to-end system testing and fix critical bugs | MUST HAVE | CS-021 | Snehitha Krishna , Joshitha Mugunthan , Manasa Barik | 6 | 3 - Completed
Sprint 8 | Sprint 8 | CS-024 | Prepare final agile documentation, project report, and demo recording | MUST HAVE | CS-023 | Suhas Amane , Ajay Varande | 4 | 3 - Completed

## Sprint Backlog
CyberShield SOC — Sprint Backlog & Burndown
US ID | Task ID | Task Description | Start Date | End Date | Assigned To | Activity | Status | Est. Hrs | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
CS-001 | 1 | Gather functional and non-functional requirements from mentor | 05-Feb-2026 | 07-Feb-2026 | Priya Barad | Planning | 3 - Completed | 4 | 8 | 7 | 5 | 3 | 2 | 1 | 0
CS-001 | 2 | Document security use cases and threat actor personas | 05-Feb-2026 | 09-Feb-2026 | Joshitha Mugunthan | Planning | 3 - Completed | 3 | 12 | 10 | 7 | 5 | 3 | 1 | 0
CS-002 | 3 | Initialize GitHub repo, add .gitignore, set branch rules | 06-Feb-2026 | 09-Feb-2026 | Manasa Barik | Setup | 3 - Completed | 2 | 8 | 6 | 4 | 3 | 1 | 0 | 0
CS-002 | 4 | Create folder structure: /frontend /backend /docs | 06-Feb-2026 | 10-Feb-2026 | Manasa Barik | Setup | 3 - Completed | 2 | 6 | 5 | 4 | 2 | 1 | 0 | 0
CS-003 | 5 | Research and compare frontend and backend framework options | 07-Feb-2026 | 11-Feb-2026 | Trisha L | Planning | 3 - Completed | 3 | 10 | 8 | 6 | 4 | 2 | 1 | 0
CS-003 | 6 | Finalize and document chosen tech stack with justification | 07-Feb-2026 | 11-Feb-2026 | Joshitha Mugunthan | Planning | 3 - Completed | 2 | 8 | 6 | 4 | 3 | 2 | 1 | 0
CS-004 | 7 | Draft MongoDB collections: threats, users, alerts, incidents | 15-Feb-2026 | 18-Feb-2026 | Snehitha Krishna | Design | 3 - Completed | 4 | 10 | 8 | 5 | 4 | 2 | 1 | 0
CS-004 | 8 | Set up MongoDB Atlas cluster and configure access credentials | 15-Feb-2026 | 18-Feb-2026 | Ashwath | Setup | 3 - Completed | 3 | 6 | 5 | 3 | 2 | 1 | 0 | 0
CS-005 | 9 | Implement JWT token generation and refresh logic | 16-Feb-2026 | 19-Feb-2026 | Priya Barad | Coding | 3 - Completed | 6 | 8 | 7 | 5 | 3 | 2 | 1 | 0
CS-005 | 10 | Create Admin and Analyst role middleware for protected routes | 16-Feb-2026 | 19-Feb-2026 | Ashwath | Coding | 3 - Completed | 4 | 12 | 10 | 7 | 5 | 3 | 1 | 0
CS-006 | 11 | Set up Express.js server with modular route structure | 12-Feb-2026 | 15-Feb-2026 | Joshitha Mugunthan | Coding | 3 - Completed | 4 | 8 | 6 | 4 | 3 | 1 | 0 | 0
CS-006 | 12 | Connect backend to MongoDB Atlas and test CRUD operations | 12-Feb-2026 | 14-Feb-2026 | Joshitha Mugunthan | Coding | 3 - Completed | 5 | 6 | 5 | 4 | 2 | 1 | 0 | 0
CS-007 | 13 | Register and configure AbuseIPDB API key | 20-Feb-2026 | 22-Feb-2026 | Priya Barad | Setup | 3 - Completed | 1 | 10 | 8 | 6 | 4 | 2 | 1 | 0
CS-007 | 14 | Build IP lookup service and cache frequent results in DB | 20-Feb-2026 | 23-Feb-2026 | Snehitha Krishna | Coding | 3 - Completed | 6 | 8 | 6 | 4 | 3 | 2 | 1 | 0
CS-008 | 15 | Design threat event schema (type, severity, origin, timestamp) | 21-Feb-2026 | 24-Feb-2026 | Ashwath | Design | 3 - Completed | 3 | 10 | 8 | 5 | 4 | 2 | 1 | 0
CS-008 | 16 | Code simulation engine to emit randomized threat payloads | 21-Feb-2026 | 25-Feb-2026 | Ajay Varande | Coding | 3 - Completed | 8 | 6 | 5 | 3 | 2 | 1 | 0 | 0
CS-009 | 17 | Integrate Socket.IO on backend to emit on new threat events | 22-Feb-2026 | 25-Feb-2026 | Priya Barad | Coding | 3 - Completed | 5 | 8 | 7 | 5 | 3 | 2 | 1 | 0
CS-009 | 18 | Connect React frontend to Socket.IO for live data updates | 22-Feb-2026 | 24-Feb-2026 | Manasa Barik | Coding | 3 - Completed | 5 | 12 | 10 | 7 | 5 | 3 | 1 | 0
CS-010 | 19 | Integrate Leaflet.js with GeoIP data for map rendering | 02-Mar-2026 | 06-Mar-2026 | Banumathi | Coding | 3 - Completed | 7 | 8 | 6 | 4 | 3 | 1 | 0 | 0
CS-010 | 20 | Add attack markers with severity color coding on map | 02-Mar-2026 | 04-Mar-2026 | Ashwath | Coding | 3 - Completed | 4 | 6 | 5 | 4 | 2 | 1 | 0 | 0
CS-011 | 21 | Build bar/line charts for attack trends using Recharts | 26-Feb-2026 | 28-Feb-2026 | Ajay Varande | Coding | 3 - Completed | 6 | 10 | 8 | 6 | 4 | 2 | 1 | 0
CS-011 | 22 | Add severity pie chart and top-attacker leaderboard widget | 26-Feb-2026 | 01-Mar-2026 | Trisha L | Coding | 3 - Completed | 5 | 8 | 6 | 4 | 3 | 2 | 1 | 0
CS-012 | 23 | Design alert rule engine with configurable thresholds | 27-Feb-2026 | 03-Mar-2026 | Manasa Barik | Coding | 3 - Completed | 6 | 10 | 8 | 5 | 4 | 2 | 1 | 0
CS-012 | 24 | Implement real-time notification banner on dashboard | 27-Feb-2026 | 03-Mar-2026 | Priya Barad | Coding | 3 - Completed | 4 | 6 | 5 | 3 | 2 | 1 | 0 | 0
CS-013 | 25 | Map threat types to MITRE ATT&CK tactic and technique IDs | 07-Mar-2026 | 10-Mar-2026 | Ashwath | Coding | 3 - Completed | 7 | 8 | 7 | 5 | 3 | 2 | 1 | 0
CS-013 | 26 | Display MITRE tags on incident detail page | 07-Mar-2026 | 11-Mar-2026 | Ashwath | Coding | 3 - Completed | 3 | 12 | 10 | 7 | 5 | 3 | 1 | 0
CS-014 | 27 | Integrate Nmap CLI via child_process in Node.js backend | 08-Mar-2026 | 12-Mar-2026 | Ajay Varande | Coding | 3 - Completed | 6 | 8 | 6 | 4 | 3 | 1 | 0 | 0
CS-014 | 28 | Parse and store Nmap scan results in MongoDB | 08-Mar-2026 | 12-Mar-2026 | Ajay Varande | Coding | 3 - Completed | 5 | 6 | 5 | 4 | 2 | 1 | 0 | 0
CS-015 | 29 | Build IP detail page with risk score and attack history | 09-Mar-2026 | 11-Mar-2026 | Manasa Barik | Coding | 3 - Completed | 6 | 10 | 8 | 6 | 4 | 2 | 1 | 0
CS-015 | 30 | Add pagination and filtering for IP reputation table | 09-Mar-2026 | 12-Mar-2026 | Ajay Varande | Coding | 3 - Completed | 4 | 8 | 6 | 4 | 3 | 2 | 1 | 0
CS-016 | 31 | Integrate VirusTotal API for URL and QR code analysis | 12-Mar-2026 | 16-Mar-2026 | Manasa Barik | Coding | 3 - Completed | 7 | 10 | 8 | 5 | 4 | 2 | 1 | 0
CS-016 | 32 | Build scanner UI with result verdict display | 12-Mar-2026 | 14-Mar-2026 | Suhas Amane | Coding | 3 - Completed | 4 | 6 | 5 | 3 | 2 | 1 | 0 | 0
CS-017 | 33 | Set up Gemini API key and prompt engineering for SOC context | 13-Mar-2026 | 17-Mar-2026 | Priya Barad | Coding | 3 - Completed | 5 | 8 | 7 | 5 | 3 | 2 | 1 | 0
CS-017 | 34 | Build AI chat interface in React with conversation history | 13-Mar-2026 | 17-Mar-2026 | Ajay Varande | Coding | 3 - Completed | 6 | 12 | 10 | 7 | 5 | 3 | 1 | 0
CS-018 | 35 | Create knowledge.json with SOC domain Q&A pairs | 14-Mar-2026 | 17-Mar-2026 | Banumathi | Documentation | 3 - Completed | 4 | 8 | 6 | 4 | 3 | 1 | 0 | 0
CS-018 | 36 | Implement vector-based retrieval for AI context injection | 14-Mar-2026 | 18-Mar-2026 | Ashwath | Coding | 3 - Completed | 8 | 6 | 5 | 4 | 2 | 1 | 0 | 0
CS-019 | 37 | Write Dockerfile for frontend and backend services | 22-Mar-2026 | 24-Mar-2026 | Ajay Varande | DevOps | 3 - Completed | 5 | 10 | 8 | 6 | 4 | 2 | 1 | 0
CS-019 | 38 | Create docker-compose.yml with all services and volumes | 22-Mar-2026 | 25-Mar-2026 | Sadi Soni | DevOps | 3 - Completed | 4 | 8 | 6 | 4 | 3 | 2 | 1 | 0
CS-020 | 39 | Write Nginx config for reverse proxy and SSL termination | 23-Mar-2026 | 27-Mar-2026 | Manasa Barik | DevOps | 3 - Completed | 4 | 10 | 8 | 5 | 4 | 2 | 1 | 0
CS-020 | 40 | Test Nginx routing and fix CORS issues in production mode | 23-Mar-2026 | 26-Mar-2026 | Trisha L | DevOps | 3 - Completed | 3 | 6 | 5 | 3 | 2 | 1 | 0 | 0
CS-021 | 41 | Add role-conditional rendering in React components | 19-Mar-2026 | 21-Mar-2026 | Suhas Amane | Coding | 3 - Completed | 5 | 8 | 7 | 5 | 3 | 2 | 1 | 0
CS-021 | 42 | Test Admin vs Analyst view with different JWT tokens | 19-Mar-2026 | 21-Mar-2026 | Joshitha Mugunthan | Testing | 3 - Completed | 3 | 12 | 10 | 7 | 5 | 3 | 1 | 0
CS-022 | 43 | Add compound indexes on threat and alert collections | 27-Mar-2026 | 30-Mar-2026 | Banumathi | Optimization | 3 - Completed | 5 | 8 | 6 | 4 | 3 | 1 | 0 | 0
CS-022 | 44 | Benchmark query times before and after indexing | 27-Mar-2026 | 30-Mar-2026 | Manasa Barik | Testing | 3 - Completed | 3 | 6 | 5 | 4 | 2 | 1 | 0 | 0
CS-023 | 45 | Write test cases for all major API endpoints | 28-Mar-2026 | 30-Mar-2026 | Ajay Varande | Testing | 3 - Completed | 6 | 10 | 8 | 6 | 4 | 2 | 1 | 0
CS-023 | 46 | Conduct user acceptance testing and log defect report | 28-Mar-2026 | 2026-03-30 | Snehitha Krishna | Testing | 3 - Completed | 5 | 8 | 6 | 4 | 3 | 2 | 1 | 0
CS-024 | 47 | Write final project report with architecture diagrams | 29-Mar-2026 | 2026-03-30 | Sadi Soni | Documentation | 3 - Completed | 5 | 10 | 8 | 5 | 4 | 2 | 1 | 0
CS-024 | 48 | Record project demo video and upload to shared drive | 29-Mar-2026 | 2026-03-30 | Snehitha Krishna | Documentation | 3 - Completed | 3 | 6 | 5 | 3 | 2 | 1 | 0 | 0

## Stand-Up Meetings
CyberShield SOC — Stand-Up Meeting Log (Mon & Thu)
Sprint | Date | Day | Impediments / Blockers | Action Taken | Raised By
Sprint 1 | 05-Feb-2026 | Thursday | Disagreement on whether to use REST or GraphQL for the backend API | Team voted and agreed on REST with Express.js after reviewing project complexity | Suhas Amane
Sprint 1 | 09-Feb-2026 | Monday | Unclear which MongoDB Atlas tier to use for free deployment | Researched Atlas free tier limits; confirmed M0 cluster is sufficient for project scope | Banumathi
Sprint 2 | 12-Feb-2026 | Thursday | JWT secret key accidentally pushed to GitHub public repo | Revoked the key immediately, added .env to .gitignore, rotated credentials | Ashwath
Sprint 2 | 16-Feb-2026 | Monday | MongoDB connection timing out intermittently during development | Switched to connection pooling and added retry logic in the DB config module | Banumathi
Sprint 3 | 19-Feb-2026 | Thursday | AbuseIPDB API returning 429 Too Many Requests errors | Added caching layer in Node.js to store results for 1 hour and reduce API calls | Joshitha Mugunthan
Sprint 3 | 23-Feb-2026 | Monday | Socket.IO events firing twice due to duplicate event listeners | Debugged event registration logic; moved listener setup to useEffect cleanup | Sadi Soni
Sprint 4 | 26-Feb-2026 | Thursday | Leaflet map not rendering correctly on certain screen resolutions | Fixed CSS height issue on map container; added responsive breakpoints | Manasa Barik
Sprint 4 | 02-Mar-2026 | Monday | Recharts data not updating in real time when new threats arrive | Switched from static data prop to state-driven data with Socket.IO listener | Sadi Soni
Sprint 5 | 05-Mar-2026 | Thursday | Nmap command execution blocked in cloud environment sandbox | Configured Nmap to run in local dev mode; flagged cloud limitation in documentation | Sadi Soni
Sprint 5 | 09-Mar-2026 | Monday | MITRE ATT&CK dataset CSV too large to load in memory at startup | Parsed and imported relevant MITRE entries into MongoDB on first run only | Joshitha Mugunthan
Sprint 6 | 12-Mar-2026 | Thursday | VirusTotal API quota exhausted after bulk URL testing | Implemented rate-limited queue for scanner requests; added usage counter to UI | Joshitha Mugunthan
Sprint 6 | 16-Mar-2026 | Monday | Gemini API responses too slow for real-time chat feel | Added streaming response mode and typing indicator to improve perceived speed | Trisha L
Sprint 7 | 19-Mar-2026 | Thursday | Docker build failing due to missing Node.js version in base image | Pinned Node.js to v18-alpine in Dockerfile; updated docker-compose accordingly | Ajay Varande
Sprint 7 | 23-Mar-2026 | Monday | Nginx returning 502 Bad Gateway after container restart | Fixed upstream server name in nginx.conf to match Docker service name | Priya Barad
Sprint 8 | 26-Mar-2026 | Thursday | Several API endpoints not covered in end-to-end test suite | Assigned each team member 2 endpoints to write test cases for; merged by Thursday | Sadi Soni
Sprint 8 | 30-Mar-2026 | Monday | Final report section on architecture missing detailed diagrams | Ashwath and Trisha drafted draw.io diagrams; added to report before submission | Suhas Amane

## Sprint Retrospective
CyberShield SOC — Sprint Retrospective
Sprint # | Sprint | Start Date | End Date | Participants | Start Doing | Stop Doing | Continue Doing | Action Items
1 | Sprint 1 | 05-Feb-2026 | 11-Feb-2026 | Trisha L , Sadi Soni , Banumathi , Suhas Amane , Snehitha Krishna | Write unit tests alongside each feature as we build | Committing directly to main without creating a feature branch | Weekly mentor check-ins before sprint review | Set up branch protection on GitHub; enforce PR reviews from next sprint
2 | Sprint 2 | 12-Feb-2026 | 18-Feb-2026 | Priya Barad , Ashwath , Sadi Soni , Snehitha Krishna , Suhas Amane , Banumathi | Use Postman collections for API testing so all members can run tests | Hardcoding API keys inside source files | Daily async updates on WhatsApp group for blockers | Move all secrets to .env file; update .gitignore and rotate compromised keys
3 | Sprint 3 | 19-Feb-2026 | 25-Feb-2026 | Trisha L , Ajay Varande , Banumathi , Joshitha Mugunthan , Snehitha Krishna , Ashwath | Add loading states and error boundaries to all async React components | Ignoring console warnings during development | Socket.IO integration pattern established this sprint — keep reusing it | Create shared component library for dashboard widgets to reduce duplication
4 | Sprint 4 | 26-Feb-2026 | 04-Mar-2026 | Ajay Varande , Banumathi , Trisha L , Manasa Barik | Plan UI/UX review sessions midway through each sprint | Merging frontend and backend changes simultaneously without integration testing | Recharts + Socket.IO real-time update pattern works well; continue using it | Add a staging environment to test integrations before pushing to production
5 | Sprint 5 | 05-Mar-2026 | 11-Mar-2026 | Joshitha Mugunthan , Ajay Varande , Sadi Soni , Trisha L | Document all external API integrations with sample request/response examples | Running Nmap scans in production environment without isolation | MITRE ATT&CK tagging adds good context; expand to more threat types | Isolate Nmap module in a sandboxed Docker container for safety
6 | Sprint 6 | 12-Mar-2026 | 18-Mar-2026 | Priya Barad , Trisha L , Manasa Barik , Snehitha Krishna , Suhas Amane | Set up response caching for all heavy AI and external API calls | Testing AI responses manually — needs automated evaluation | Gemini streaming improves UX; apply same pattern to other slow APIs | Write a simple eval script to benchmark AI assistant response quality
7 | Sprint 7 | 19-Mar-2026 | 25-Mar-2026 | Snehitha Krishna , Manasa Barik , Ashwath , Suhas Amane | Tag Docker images with version numbers before each deployment | Rebuilding entire Docker stack for minor config changes | Docker Compose makes environment setup fast — keep using it | Write a deploy.sh script to automate container rebuild and restart steps
8 | Sprint 8 | 26-Mar-2026 | 2026-03-30 | Manasa Barik , Joshitha Mugunthan , Banumathi , Priya Barad | Start documentation and test writing in parallel with development, not after | Leaving bug fixes to the last sprint — causes unnecessary pressure | Daily standups on Mon & Thu helped maintain visibility throughout project | Archive GitHub repo, upload demo to Google Drive, share report with mentor